## Sheet1
Task | Category | Start | Duration | Delay | Adjusted Start | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30
Collect soil samples | Soil Texture | 0 | 1 | 0 | 0 | Day 1: Collect soil samples
Perform soil analysis | Soil Texture | 1 | 2 | 0 | 2 | Day 2: Perform soil analysis
Interpret texture results | Soil Texture | 1 | 1 | 0 | 2 | Day 3: Interpret texture results
Conduct compaction test | Soil Compaction | 3 | 1 | 0 | 3 | Day 4: Conduct compaction test
Identify compacted zones | Soil Compaction | 4 | 1 | 0 | 4 | Day 5: Identify compacted zones
Suggest intervention | Soil Compaction | 5 | 1 | 0 | 5 | Day 6: Suggest intervention
List required equipment | Equipment Availability | 6 | 1 | 0 | 6 | Day 7: List required equipment
Check availability | Equipment Availability | 6 | 1 | 0 | 7 | Day 7: Check availability
Arrange procurement | Equipment Availability | 7 | 1 | 0 | 8 | Day 8: Arrange procurement