## Gantt Chart
Task | Category | Start | Duration | Delay | Adjusted Start | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25
Green Manuring Planning | Planning | 0 | 5 | 0 | 0
Time Window | Planning | 5 | 3 | 0 | 5
Crop Suitability | Planning | 8 | 4 | 0 | 8
Labour & Equipment | Planning | 12 | 4 | 0 | 12